## Sheet1
Task | Start Date | End Date | Assigned To | Status
Prepare delivery schedule | 2025-05-02 | 2025-05-02 | Hassan | Completed
Assign delivery staff | 2025-05-03 | 2025-05-03 | Amna | Completed
Load products | 2025-05-04 | 2025-05-04 | Zain | In Progress
Start delivery | 2025-05-05 | 2025-05-05 | Usman | Pending
Confirm delivery | 2025-05-06 | 2025-05-06 | Zara | Pending
Collect feedback | 2025-05-07 | 2025-05-07 | Fatima | Pending