## Sheet1
Task | Start Date | End Date | Assigned To | Status
Check current inventory levels | 2025-05-01 | 2025-05-01 | Ali | Completed
Forecast demand | 2025-05-02 | 2025-05-02 | Fatima | Completed
Create purchase order | 2025-05-03 | 2025-05-03 | Zara | In Progress
Send order to supplier | 2025-05-04 | 2025-05-05 | Ahmed | Pending
Receive and inspect inventory | 2025-05-06 | 2025-05-06 | Sara | Pending
Update stock records | 2025-05-07 | 2025-05-07 | Ali | Pending