## Inventory Refill
Task | Start Date | End Date | Assigned To | Status
Check current inventory levels | 2025-05-01 | 2025-05-01 | Ali | Completed
Forecast demand | 2025-05-02 | 2025-05-02 | Fatima | Completed
Create purchase order | 2025-05-03 | 2025-05-03 | Zara | In Progress
Send order to supplier | 2025-05-04 | 2025-05-05 | Ahmed | Pending
Receive and inspect inventory | 2025-05-06 | 2025-05-06 | Sara | Pending
Update stock records | 2025-05-07 | 2025-05-07 | Ali | Pending

## Delivery Flow
Task | Start Date | End Date | Assigned To | Status
Prepare delivery schedule | 2025-05-02 | 2025-05-02 | Hassan | Completed
Assign delivery staff | 2025-05-03 | 2025-05-03 | Amna | Completed
Load products | 2025-05-04 | 2025-05-04 | Zain | In Progress
Start delivery | 2025-05-05 | 2025-05-05 | Usman | Pending
Confirm delivery | 2025-05-06 | 2025-05-06 | Zara | Pending
Collect feedback | 2025-05-07 | 2025-05-07 | Fatima | Pending

## Logistics Management
Task | Start Date | End Date | Assigned To | Status
Coordinate with vendors | 2025-05-01 | 2025-05-01 | Kamran | Completed
Arrange transportation | 2025-05-02 | 2025-05-02 | Fariha | Completed
Track shipment | 2025-05-03 | 2025-05-03 | Yasir | In Progress
Update shipment records | 2025-05-04 | 2025-05-04 | Ali | Pending
Schedule unloading | 2025-05-05 | 2025-05-05 | Sana | Pending
Complete delivery checklist | 2025-05-06 | 2025-05-06 | Rida | Pending